## Sheet1
FEATURE | EPIC | STORIES | DESCRIPTION | POD | SPRINT
MY ACCOUNT | LOGIN | Ability to login to the system and provide right access to resources | There will be a basic login page, After successful login user will be redirected to their respective operations. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 1
| UPDATE PASSWORD | Enables the User to update their passord | User can update their passowrd by providing their credentials. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 1
ADMIN MODULE | ADD PROFESSOR | Enables the Admin to Add new Professor. | Admin can add new Professor in the Database, assigning a course to the Professor. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 6
| DELETE PROFESSOR | Enables the Admin to Remove Professor. | Admin can remove Professor once the Professor activities have been completed. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 6
| ADD COURSE | Enables the Admin to Add new Course. | Admin can add new Course in the Database with details like Course ID, Course Name and Course Fees. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 7
| REMOVE COURSE | Enables the Admin to remove Course. | Admin can Remove Course from the Database. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 7
| APPROVE STUDENT REGISTRATION | Enables the Admin to Approve Student's Registration | Admin has to Approve the Student upon Registering, for the Student that matches the Requirements for the Institute. Student cannot login before the Admin has given the Approval. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 8
| STUDENT COURSE PAYMENT STATUS | Enables the Admin to check student payment status towards course. | Admin can check the Course payment satus whther the student has made payment for the Courses he/she has enrolled to. | POD 1 (Bheem, Shiva, Dinesh) | Sprint 8
| SEND NOTIFICATIONS | Enables the Admin to send out Notifications | Admin can send Notifications to Students regarding new Courses and etc. | POD 1 (Bheem, Shiva, Dinesh) | Yet to be Completed
PROFESSOR MODULE | VIEW ENROLLED STUDENTS | Enables the professor to view enrolled students. | Professor can view all the Enrolled students to the Course the Professor has been assigned. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 2
| ADD GRADES | Enables the professor to Add grades to the students. | The professor has to assigne a grade to the Student with Respective Course ID he is teaching. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 2
STUDENT MODULE | VIEW COURSE | Enables the Student to view courses before enrolling. | Student can view courses with details like Course ID, Course Name and Course Fee and can enrolle the courses. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 3
| ENROLL COURSE | Enables the Student to enroll courses. | Student can add courses by proving a Course ID. Student can add upto 4 Courses. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 4
| DROP COURSE | Enables the Student to drop courses. | Student can Drop courses by providing a Course ID | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 4
| MAKE PAYMENT | Enables the Student to make payment. | Student can make payment for all the courses he has selected. Student has to provide the requested Card details to make the Payment. Here all the Course Fees will be summed and displayed to the student before making the Payment. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 5
| VIEW REPORT CARD | Enables the Student to view their report card. | Stuident can view their Rpoet card for all the Enrolled Courses once the Respective Professor has assigined the Grade to the Student. | POD 2 (Deepika, Shiva Amancha, Rajnish) | Sprint 5